## READ ME
Corbit X: SharePoint list updates after the go-live briefing (1 February 2027)
Your lists keep working as they are: no list or column names changed and no columns were added.
A list that has items overrides the page's built-in wording, so the corrected wording appears on your page only once these rows are updated.
Each sheet is named like the list. Only rows that changed are shown. Column ACTION (last) says what to do:
UPDATE: open the item with the same Order number (or the same Title) and paste the new values.
ADD: create a new item with these values (Order is the position it should take).
REMOVE: set IsActive to No on the item with this Order (or delete it).
Do not forget Page Settings: GoLive must become 2027-02-01T00:00:00+00:00.
The sheet CHANGES lists every change in words.

## CHANGES
List | Order | Action | Item (title before) | What changed (column: before => after)
Kukua Messages | 1 | UPDATE | welcome | Text: Hello! I'm Kukua, your Corbit X guide. Over the coming months, I'll help you discover what Corbit X means for our customers, branches, and t… => Hello! I'm Kukua, your Corbit X guide. Between now and go-live on Monday 1 February 2027, I'll help you discover what Corbit X means for our…
Kukua Messages | 7 | UPDATE | chatFallback | Text: Good question! I don't have an answer for that one yet. Try one of the suggested questions, or check with your Branch Operations Supervisor. => Good question! I don't have an answer for that one yet. Try one of the suggested questions, or check the guide, ask your champion, and log a…
Section Intros | 1 | UPDATE | highlights | Text: Look how far we've come together! These numbers show the energy our people are putting into Corbit X. => Look how far we've come together! Our simulation score rose from 51% to 93.4%, and confidence has nearly doubled.
Section Intros | 5 | UPDATE | next | Text: So, what's next? Here are the steps that will take us from today all the way to go-live. => So, what's next? Here are the five steps that take us from today to go-live on Monday 1 February 2027.
Journey Stages | 1 | UPDATE | Understanding the Transition | PanelIntro: Old account numbers will continue to be accepted for more than six months after go-live. => Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and a custome…
Journey Stages | 2 | UPDATE | Chequebook Transition | PanelIntro: Cheques bearing old account numbers are accepted for six months after go-live, subject to the usual checks. After six months, these cheques … => Cheques bearing old account numbers are accepted for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. … PanelPoints: Accept ¦ Accept old-number cheques for six months after go-live, subject to the usual checks. Encourage ¦ Encourage customers to request new… => Accept ¦ Accept old-number cheques until 2 August 2027, subject to the usual checks. Encourage ¦ Encourage customers to request new chequebo…
Journey Stages | 4 | UPDATE | Operational Preparedness | PanelIntro: On the Sunday immediately before go-live, BOSs will open the branch day. All branch staff will take part in live transaction and channel che… => On Sunday 31 January 2027, the day before go-live, BOSs will open the branch day. All branch staff will take part in live transaction and ch… PanelPoints: Test ¦ Test deposits, branch transactions, ATMs, the mobile app and other instructed channels. Real funds ¦ These are real transactions with… => Friday 29 January ¦ Finish all transactions by the 2:00pm cut-off, balance cash and vault, clear suspense and run the final end of day. Test…
Journey Stages | 6 | UPDATE | Keeping Business Moving | PanelIntro: During the static data freeze in the week before go-live and the first three days after go-live, account opening is unavailable in Flexcube … => During the static data freeze in the week before go-live and the first three days after go-live (Monday 1 to Wednesday 3 February), account … PanelPoints: Start ¦ Start in Newgen. Collect all required documents. Receive ¦ Receive deposits through the designated GL. Record and monitor every depo… => Start ¦ Start in Newgen. Collect all required documents. Receive ¦ Receive deposits through the designated GL. Record and monitor every depo…
Highlights | 1 | UPDATE | Staff bank-wide | Title: Staff bank-wide => Overall simulation score (95% go-live gate) Group: No. of Staff => Overall readiness Icon: users => sim Value: 2500 => 93.4 Suffix: + => % ShowBar: No => Yes
Highlights | 2 | UPDATE | Project completion rate | Title: Project completion rate => Staff confident in go-live readiness (45% at BSIM 1) Group: No. of Staff => Overall readiness Icon: users => sim Value: 94 => 85
Highlights | 3 | UPDATE | Champions across the bank | Title: Champions across the bank => Logged in at BSIM 4 Group: Staff Engagement => System and support Icon: heart => check Value: 30 => 99.8 Suffix: + => %
Highlights | 4 | UPDATE | Bank-wide roadshows | Title: Bank-wide roadshows => Tickets fixed the same day Group: Staff Engagement => System and support Icon: heart => check Value: 2 => 96 Suffix: => %
Highlights | 5 | UPDATE | Business simulations | Title: Business simulations => Branches ready Group: Business Simulation => Branches Icon: sim => users Value: 3 => 94 Suffix: => %
Highlights | 6 | UPDATE | Staff confidence | Title: Staff confidence => Business simulations completed Group: Business Simulation => Branches Icon: sim => users Value: 68 => 4 Suffix: % => ShowBar: Yes => No
Customer Changes | 1 | UPDATE | At the Counter | Points: Serve customers faster Full 360° view in one screen Credits and salaries at speed => Quicker service at the counter 360-degree customer view at the teller point Faster credit and salary processing
Customer Changes | 2 | UPDATE | Account Numbers | Points: New format, same CIF: add “00” in front Old numbers usable during the transition Longer format = more security => New 13-digit account numbers Customer CIF gains “00” in front Old numbers still work for more than six months
Customer Changes | 3 | UPDATE | Cheque Books | Points: Order new books within 182 days Current leaves accepted meanwhile Books 5+ years old won't migrate => Reorder within the first 182 days Current leaves accepted in the meantime Books over 5 years old are not migrated
Customer Changes | 4 | UPDATE | Statements | Points: 0–12 months: instant via Corbit X 12 months+: from secure backup Cleaner, faster request process => 0–12 months: straight from Corbit X Older statements, back to account opening: from stored backup
Training Media | 4 | UPDATE | Account opening during the freeze | Description: Start in Newgen, finalise from Thursday => Start in Newgen, finalise from Thursday 4 February
What's Next | 1 | UPDATE | Complete your training | Title: Complete your training => Keep your skills sharp Label: Keep learning => 26 Oct – 23 Dec Text: Finish your end-user training modules and practise the new processes. => Practise twice a week. Branches 7:15 – 8:15 am; departments one hour, two days a week.
What's Next | 2 | UPDATE | Business simulations | Title: Business simulations => Rest and recharge Label: Practise => 24 Dec – 3 Jan Text: Take part in simulations to build confidence before go-live. => No scheduled sessions. The Corbit X portal stays open if you want a refresher. Icon: sim => heart
What's Next | 3 | UPDATE | Meet your champion | Title: Meet your champion => Get go-live ready Label: Connect => 4 – 22 Jan Text: Our 30+ Corbit X champions are on hand to answer questions locally. => One hour every working day, then certification for your role. Icon: users => check
What's Next | 4 | UPDATE | Sunday live checks | Title: Sunday live checks => Final systems check Label: Get ready => 11 – 17 Jan Text: Join the live transaction and channel checks on the Sunday before go-live. => Data migration and validation, then the business simulation on Sunday 17 January. Icon: check => sim
What's Next | 5 | UPDATE | Same warm welcome | Title: Same warm welcome => Lift-off! Label: Go-live => Mon 1 Feb 2027 Text: Serve every customer with confidence on Corbit X. => Corbit X goes live. Arrive early, log in and welcome every customer.
Daily Tips | 9 | ADD | Stuck? Check the guide, ask your champion, log a Command Centre ticket, then update the customer. | Title: => Stuck? Check the guide, ask your champion, log a Command Centre ticket, then update the customer.
Daily Tips | 10 | ADD | The bank never asks for a PIN, password or OTP. Never share your login. | Title: => The bank never asks for a PIN, password or OTP. Never share your login.
FAQs | 3 | UPDATE | How will customers benefit? | Answer: Faster service at the counter, a full 360° view of the customer on one screen, credits and salaries at speed, instant statements for the las… => Quicker service at the counter, a 360-degree customer view at the teller point, faster credit and salary processing, statements for the last…
FAQs | 4 | UPDATE | What changes for branches? | Answer: A few things to know: new account numbers (look them up in Corbit X and share them), cheque and chequebook changes, a short pause in account… => A few things to know: new account numbers (look them up in Corbit X and share them), cheque and chequebook changes, a short pause in account…
FAQs | 5 | UPDATE | Where can I find guides? | Answer: Right here! There are six guides on my journey. Tap 'View Guide' on any stop to see the full poster. => Right here! There are six guides on my journey. Tap 'View Guide' on any stop to see the full poster. You will also find guides, staff FAQs a…
FAQs | 6 | UPDATE | Who can I contact for support? | Answer: Start with your Branch Operations Supervisor (BOS). For anything else, consult the relevant internal team. Programme support contacts will b… => Check the guide or FAQ first, then ask your champion or team lead. If you are still stuck, log a Command Centre ticket with a screenshot, an…
FAQs | 7 | UPDATE | Will old account numbers still work? | Answer: Yes. Old account numbers will continue to be accepted for more than six months after go-live. The new format keeps the same CIF with “00” ad… => Yes. Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and the …
FAQs | 8 | UPDATE | Can we open accounts during the upgrade? | Answer: Account opening pauses during the static data freeze and the first three days after go-live. Start the application in Newgen, receive deposi… => Account opening pauses during the static data freeze and the first three days after go-live (Monday 1 to Wednesday 3 February). Start the ap…
FAQs | 9 | UPDATE | How do statements work in Corbit X? | Answer: Statements for the last 0–12 months are instant via Corbit X. Older statements (12 months+) come from secure backup, through a cleaner, fast… => Statements for the last 12 months come straight from Corbit X. Older statements, back to when the account was opened, come from stored backu…
FAQs | 10 | UPDATE | What about cheques? | Answer: Cheques with old account numbers are accepted for six months after go-live, subject to the usual checks. Chequebooks recorded more than five… => Cheques with old account numbers are accepted for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. Che…
FAQs | 11 | UPDATE | What happens on the Sunday before go-live? | Answer: BOSs open the branch day and all branch staff run live transaction and channel checks with real funds. Don't close the branch day or run end… => On Sunday 31 January 2027, BOSs open the branch day and all branch staff run live transaction and channel checks with real funds. Don't clos…
FAQs | 12 | ADD | When does Corbit X go live? | Title: => When does Corbit X go live? Answer: => Corbit X goes live on Monday 1 February 2027, in every branch and department at the same time. The final cut-off on the current system is Fr… Keywords: => when date go-live golive live start monday february 2027 cut-off Suggested: => No ActionLabel: => See the guide ActionTarget: => stop:4
FAQs | 13 | ADD | How do I read the new account number? | Title: => How do I read the new account number? Answer: => It has 13 digits. Digits 1 and 2 are the currency (00 cedi, 01 dollar, 02 pound, 03 euro). Digit 3 is the customer type (1 individual, 2 non… Keywords: => account number new 13 digit digits currency customer type format read cif Suggested: => No
FAQs | 14 | ADD | What if someone asks a customer for their OTP? | Title: => What if someone asks a customer for their OTP? Answer: => The bank never asks for a PIN, password or OTP, and you must never share your login. Tell the customer, and report anything suspicious to Fr… Keywords: => otp pin password fraud scam suspicious login share Suggested: => No
Featured Guides | 4 | UPDATE | Keep the Welcome. Start the Process. | KukuaCommentary: Account opening pauses briefly, but our welcome never does. Start in Newgen and finalise from Thursday. => Account opening pauses briefly, but our welcome never does. Start in Newgen and finalise from Thursday 4 February.
Announcements | 1 | UPDATE | Six Corbit X staff guides are now available | Title: Six Corbit X staff guides are now available => Go-live is now Monday 1 February 2027 Body: Explore them all on Kukua's journey, from account numbers to go-live readiness. => Go-live has moved to accommodate other important transactions the Bank is undertaking. The extra weeks help us go live with even greater con…
Announcements | 2 | UPDATE | Look-up process included in training | Title: Look-up process included in training => Six Corbit X staff guides are now available Body: Training covers how to find a customer's new account number in Corbit X. => Explore them all on Kukua's journey, from account numbers to go-live readiness.
Announcements | 3 | UPDATE | Printing new account numbers | Title: Printing new account numbers => Look-up process included in training Body: Guidance on printing new account numbers for customers will follow. => Training covers how to find a customer's new account number in Corbit X.
Page Settings | 1 | UPDATE | GoLive | Value: 2027-02-08T00:00:00+00:00 => 2027-02-01T00:00:00+00:00
Page Settings | 2 | UPDATE | CurrentPhase | Value: 1 => 0
Page Settings | 3 | UPDATE | AnnouncementTitle | Value: The Corbit X Staff Guide series is live => Go-live is now Monday 1 February 2027
Page Settings | 4 | UPDATE | AnnouncementBody | Value: Six practical guides now cover customer welcomes, account opening during the upgrade, new account numbers, cheques and the Sunday live check… => Go-live has moved to accommodate other important transactions the Bank is undertaking. The extra weeks help us go live with even greater con…
Page Settings | 5 | UPDATE | AnnouncementDate | Value: 2026-10-19 => 2026-10-23
Page Settings | 6 | UPDATE | FiguresAreIllustrative | Value: Yes => No
Staff Guides | 2 | UPDATE | Keep the Welcome. Start the Process. | Intro: During the static data freeze in the week before go-live and the first three days after go-live, account opening is unavailable in Flexcube … => During the static data freeze in the week before go-live and the first three days after go-live (Monday 1 to Wednesday 3 February 2027), acc… Steps: Start ¦ Start in Newgen. Collect all required documents. Receive ¦ Receive deposits through the designated GL. Record and monitor every depo… => Start ¦ Start in Newgen. Collect all required documents. Receive ¦ Receive deposits through the designated GL. Record and monitor every depo…
Staff Guides | 3 | UPDATE | Old Number? We Can Help! | Intro: Old account numbers will continue to be accepted for more than six months after go-live. => Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and a custome…
Staff Guides | 4 | UPDATE | New Chapter. New Chequebook. | Intro: Accept cheques bearing old account numbers for six months after go-live, subject to the usual checks. After six months, these cheques will n… => Accept cheques bearing old account numbers for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. After … Steps: Accept ¦ Accept old-number cheques for six months after go-live, subject to the usual checks. Encourage ¦ Encourage customers to request new… => Accept ¦ Accept old-number cheques until 2 August 2027, subject to the usual checks. Encourage ¦ Encourage customers to request new chequebo…
Staff Guides | 6 | UPDATE | Sunday Checks. Monday Confidence. | Intro: On the Sunday immediately before go-live, BOSs will open the branch day. All branch staff will participate in live transaction and channel c… => On Sunday 31 January 2027, the day before go-live, BOSs will open the branch day. All branch staff will participate in live transaction and … Steps: Test ¦ Test deposits, branch transactions, ATMs, the mobile app and other instructed channels. Real Funds ¦ These are REAL transactions with… => Test ¦ Test deposits, branch transactions, ATMs, the mobile app and other instructed channels. Real Funds ¦ These are REAL transactions with…
Programme Phases | 1 | UPDATE | Awareness | Title: Awareness => Keep your skills sharp Icon: megaphone => cap When: Now – ongoing => 26 Oct – 23 Dec 2026 Description: Building understanding of what Corbit X is, why we are moving and what changes for customers and staff. => Regular practice, so everyone is confident on Corbit X before go-live. Focus: Read the six Corbit X Staff Guides Share the key messages in team huddles Know where to find answers in the Knowledge Hub => Practise twice a week, every week Branches: 7:15 – 8:15 am. Departments: one hour, two days a week Final session: Wednesday 23 December Materials: p ¦ p1 p ¦ p3 h ¦ updates h ¦ faq => h ¦ videos h ¦ qrc p ¦ p3
Programme Phases | 2 | UPDATE | Training | Title: Training => Rest and recharge Icon: cap => heart When: Before go-live => 24 Dec 2026 – 3 Jan 2027 Description: Hands-on learning so every colleague can work confidently in Corbit X, including the new account-number look-up process. => A break to celebrate with your loved ones. There are no scheduled sessions. Focus: Complete your assigned training modules Practise looking up new account numbers Keep the quick reference cards close => No scheduled sessions Celebrate with your loved ones The Corbit X portal stays open if you want a refresher Materials: h ¦ videos h ¦ qrc p ¦ p3 p ¦ p2 => h ¦ faq h ¦ videos
Programme Phases | 3 | UPDATE | Readiness Testing | Title: Readiness Testing => Get go-live ready When: Go-live weekend => 4 – 22 Jan 2027 Description: Live transaction and channel checks on the Sunday immediately before go-live, led by BOSs with all branch staff participating. => One hour every working day (15 days): a refresher, then certification for your role. Focus: Test deposits, branch transactions, ATMs and the mobile app Real transactions with real funds: follow controls Do not close the branch day o… => Branches: 7:15 – 8:15 am. Departments: time set by your HoD Complete your refresher, then get certified by 22 January Champions check in on … Materials: p ¦ p6 h ¦ dates h ¦ contacts => h ¦ videos h ¦ qrc p ¦ p3 p ¦ p2
Programme Phases | 4 | UPDATE | Go-Live | Title: Go-Live => Final systems check Icon: rocket => chart When: Go-live Monday => 11 – 17 Jan 2027 Description: Corbit X opens for business. Continue the same branch day from Sunday and lead every interaction with a warm welcome. => Before lift-off, we make sure every record lands safely in Corbit X. Then we fly a full practice mission together on Sunday 17 January. Focus: Run end of day at close of business on Monday Start account-opening requests in Newgen Smile. Check. Serve. => Mon 11 Jan: static data migration Wed 13 – Fri 15 Jan: data validation. Sat 16 Jan: financial validation Sun 17 Jan: business simulation (mi… Materials: p ¦ p1 p ¦ p2 p ¦ p6 => h ¦ dates h ¦ contacts
Programme Phases | 5 | UPDATE | Customer Support | Title: Customer Support => Lift-off weekend Icon: heart => rocket When: First weeks after go-live => Fri 29 Jan – Mon 1 Feb 2027 Description: Helping customers through the change: new account numbers, cheques, chequebooks and account opening. => Friday 29 January is the last day on the current system, with a 2:00pm cut-off. Sunday 31 January is the live-check day. Monday 1 February i… Focus: Look up and share new account numbers at every interaction Accept old-number cheques subject to the usual checks Help customers with affecte… => Fri 29 Jan: finish all transactions by 2:00pm, balance cash and vault, run the final end of day Sun 31 Jan: BOSs open the branch day and all… Materials: p ¦ p3 p ¦ p4 p ¦ p5 h ¦ contacts => p ¦ p6 p ¦ p1 h ¦ dates
Programme Phases | 6 | UPDATE | Stabilization | Title: Stabilization => After go-live Icon: chart => heart When: Six months after go-live => From Mon 1 Feb 2027 Description: Embedding new ways of working, closing out transition arrangements and building on the platform. => Support for customers and colleagues through the first days, weeks and months. Focus: Old-number cheques no longer accepted after six months Keep encouraging use of new account numbers Share feedback to help us improve => Mon 1 – Wed 3 Feb: start account openings in Newgen. Accounts are finalised from Thu 4 Feb First weeks: hypercare, with daily check-ins, the… Materials: p ¦ p4 h ¦ dates h ¦ updates h ¦ faq => p ¦ p2 p ¦ p3 p ¦ p4 p ¦ p5 h ¦ contacts
Hub FAQs | 1 | UPDATE | Will customers' old account numbers still work after go-live? | Title: Will customers' old account numbers still work after go-live? => When does Corbit X go live? Answer: Yes. Old account numbers will continue to be accepted for more than six months after go-live. Look up the new number in Corbit X using the p… => Corbit X goes live on Monday 1 February 2027, in every branch and department at the same time. The final cut-off on the current system is Fr… PosterId: p3 => p6
Hub FAQs | 2 | UPDATE | Can customers still use cheques that show their old account number? | Title: Can customers still use cheques that show their old account number? => Will customers' old account numbers still work after go-live? Answer: Yes, for six months after go-live, subject to the usual checks. After six months these cheques will no longer be accepted, so encourage cust… => Yes. Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and the … PosterId: p4 => p3
Hub FAQs | 3 | UPDATE | What about chequebooks recorded more than five years ago? | Title: What about chequebooks recorded more than five years ago? => Can customers still use cheques that show their old account number? Answer: These chequebooks will not be migrated to Corbit X and can no longer be used. Affected customers have been notified. Explain the position wi… => Yes, for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. After that date these cheques will no longer… PosterId: p5 => p4
Hub FAQs | 4 | UPDATE | Can we open new accounts during the upgrade? | Title: Can we open new accounts during the upgrade? => What about chequebooks recorded more than five years ago? Answer: Account opening is unavailable in Flexcube 11.1 and Corbit X during the static data freeze (the week before go-live) and for the first three… => These chequebooks will not be migrated to Corbit X and can no longer be used. Affected customers have been notified. Explain the position wi… PosterId: p2 => p5
Hub FAQs | 5 | UPDATE | What happens on the Sunday before go-live? | Title: What happens on the Sunday before go-live? => Can we open new accounts during the upgrade? Answer: BOSs will open the branch day and all branch staff take part in live transaction and channel checks: deposits, branch transactions, ATMs, th… => Account opening is unavailable in Flexcube 11.1 and Corbit X during the static data freeze (the week before go-live) and for the first three… PosterId: p6 => p2
Hub FAQs | 6 | UPDATE | What should I do if I'm not sure how to answer a customer? | Title: What should I do if I'm not sure how to answer a customer? => What happens on the Sunday before go-live? Answer: Pause and check before answering. Consult the relevant internal team, or find the guidebook or procedure in the repository. Never let a syst… => On Sunday 31 January 2027, BOSs will open the branch day and all branch staff take part in live transaction and channel checks: deposits, br… PosterId: p1 => p6
Hub FAQs | 7 | UPDATE | Will new account numbers be printed for customers? | Title: Will new account numbers be printed for customers? => What should I do if I'm not sure how to answer a customer? Answer: Guidance on printing new account numbers will follow. Until then, look up and share the new number at every interaction. => Pause and check before answering. Consult the relevant internal team, or find the guidebook or procedure in the repository. Never let a syst… PosterId: p3 => p1
Hub FAQs | 8 | ADD | Will new account numbers be printed for customers? | Title: => Will new account numbers be printed for customers? Answer: => Guidance on printing new account numbers will follow. Until then, look up and share the new number at every interaction. PosterId: => p3
Hub FAQs | 9 | ADD | How do I read the new account number? | Title: => How do I read the new account number? Answer: => It has 13 digits. Digits 1 and 2 are the currency (00 cedi, 01 dollar, 02 pound, 03 euro). Digit 3 is the customer type (1 individual, 2 non… PosterId: => p3
Hub FAQs | 10 | ADD | What should I do if I'm stuck? | Title: => What should I do if I'm stuck? Answer: => Check the repository guide or FAQ, then ask your champion or team lead. If you are still stuck, log a Command Centre ticket with a screensho… PosterId: => p1
Hub FAQs | 11 | ADD | What if someone asks a customer for their OTP? | Title: => What if someone asks a customer for their OTP? Answer: => The bank never asks for a PIN, password or OTP, and you must never share your login. Tell the customer, and report anything suspicious to Fr… PosterId: => p1
Training Videos | 3 | UPDATE | Account opening during the freeze | Description: Start in Newgen, finalise from Thursday => Start in Newgen, finalise from Thursday 4 February
Quick Reference Cards | 1 | UPDATE | Account numbers | Items: + Old numbers accepted for 6+ months + Look up the new number in Corbit X + Share the new number every time => + 13 digits: currency (2), customer type (1), serial (8), check (2) + Add “00” before an old CIF + Old numbers accepted for more than six mo…
Quick Reference Cards | 2 | UPDATE | Cheques | Items: + Old-number cheques: 6 months, usual checks + Encourage new chequebook requests early - Books recorded 5+ years ago can't be used => + Old-number cheques: six months (182 days), until 2 August 2027, usual checks + Encourage new chequebook requests early - Books recorded 5+…
Quick Reference Cards | 3 | UPDATE | Account opening | Items: + Start in Newgen, collect all documents + Deposits via the designated GL + Finalise from Thursday after go-live => + Start in Newgen, collect all documents + Deposits via the designated GL + Finalise from Thursday 4 February
Quick Reference Cards | 4 | UPDATE | Go-live weekend | Items: + Sunday: live checks with real funds - No branch-day close or EOD on Sunday + Run EOD at close of business Monday => + Fri 29 Jan: finish transactions by the 2:00pm cut-off + Sun 31 Jan: live checks with real funds - No branch-day close or EOD on Sunday + M…
Quick Reference Cards | 5 | UPDATE | Every customer | Items: + Smile & serve. Keep customers informed + Listen calmly; pause and check if unsure - Never turn a customer away => + Smile & serve. Keep customers informed + Listen calmly; pause and check if unsure - Never turn a customer away - Never share your login, P…
Quick Reference Cards | 6 | ADD | BOS authorisers | Title: => BOS authorisers Items: => + KYC first (STSKYCMN): search by KYC Reference, not by status + Then CIF (STSCIF): authorise only after the KYC is done + Cheque book reque…
Project Updates | 1 | UPDATE | Staff Guide series complete | Title: Staff Guide series complete => Go-live moves to Monday 1 February 2027 Date: 2026-10-19 => 2026-10-23 Body: All six Corbit X Staff Guide posters are now available in the gallery, covering customer experience, account and chequebook transition, and … => Go-live has moved to accommodate other important transactions the Bank is undertaking. The extra weeks help us go live with even greater con…
Project Updates | 2 | UPDATE | Account-number look-up included in training | Title: Account-number look-up included in training => Staff Guide series complete Body: Training covers how to look up a customer's new account number in Corbit X. Complete your modules before go-live. => All six Corbit X Staff Guide posters are now available in the gallery, covering customer experience, account and chequebook transition, and …
Project Updates | 3 | UPDATE | Printing new account numbers | Title: Printing new account numbers => Account-number look-up included in training Body: Guidance on printing new account numbers for customers will follow. Watch this space. => Training covers how to look up a customer's new account number in Corbit X. Complete your modules before go-live.
Project Updates | 4 | ADD | Business simulation 4: 93.4% | Title: => Business simulation 4: 93.4% Date: => 2026-09-20 Body: => Our overall simulation score rose from 51% to 93.4% across four simulations, 1.6 points from the 95% go-live gate.
Project Updates | 5 | ADD | Printing new account numbers | Title: => Printing new account numbers Date: => 2026-10-19 Body: => Guidance on printing new account numbers for customers will follow. Watch this space.
Key Dates | 1 | UPDATE | Static data freeze begins | Title: Static data freeze begins => Static data migration Body: Account opening unavailable in Flexcube 11.1 and Corbit X. Start applications in Newgen. => Customer and account data moves to Corbit X. OffsetDays: -7 => -21 Format: Week => Day
Key Dates | 2 | UPDATE | Sunday live checks | Title: Sunday live checks => Data validation begins Body: BOSs open the branch day; all staff run live transaction and channel checks. => Every record checked and confirmed, Wednesday 13 to Friday 15 January. OffsetDays: -1 => -19
Key Dates | 3 | UPDATE | Corbit X go-live | Title: Corbit X go-live => Financial validation Body: Continue Sunday's branch day; run end of day at close of business. => Balances checked to the last pesewa. OffsetDays: 0 => -16 Big: Yes => No
Key Dates | 4 | UPDATE | Account opening resumes | Title: Account opening resumes => Business simulation Body: Finalise pending applications and provide account numbers. => Migration plus a full day of business replay. OffsetDays: 3 => -15 Big: No => Yes
Key Dates | 5 | UPDATE | Old-number cheques end | Title: Old-number cheques end => Final cut-off, 2:00pm Body: Cheques bearing old account numbers are no longer accepted. => Last day on the current system. Balance cash and vault, clear suspense and run the final end of day. OffsetDays: 0 => -3 OffsetMonths: 6 => 0 Format: Full => Day Big: Yes => No
Key Dates | 6 | ADD | Sunday live checks | Title: => Sunday live checks Body: => BOSs open the branch day; all staff run live transaction and channel checks. Do not close the day or run end of day. OffsetDays: => -1 OffsetMonths: => 0 Format: => Day Big: => No
Key Dates | 7 | ADD | Corbit X go-live | Title: => Corbit X go-live Body: => Arrive by 7:00am. Continue Sunday's branch day; run end of day at close of business. OffsetDays: => 0 OffsetMonths: => 0 Format: => Day Big: => Yes
Key Dates | 8 | ADD | Account opening resumes | Title: => Account opening resumes Body: => Finalise pending applications and provide account numbers. OffsetDays: => 3 OffsetMonths: => 0 Format: => Day Big: => No
Key Dates | 9 | ADD | Old-number cheques end | Title: => Old-number cheques end Body: => Six months (182 days) after go-live: cheques bearing old account numbers are no longer accepted. OffsetDays: => 182 OffsetMonths: => 0 Format: => Full Big: => Yes
Support Contacts | 1 | UPDATE | Corbit X Programme Office | Title: Corbit X Programme Office => Your champion Purpose: Programme questions and feedback => First line of help: local support and floor-walking Contact: [Add email / extension] => [Add name]
Support Contacts | 2 | UPDATE | Branch Operations Support | Title: Branch Operations Support => Command Centre Icon: shield => phoneapp Purpose: Go-live weekend and branch-day issues => Log a ticket with a screenshot: issues, fixes and coordination
Support Contacts | 3 | UPDATE | IT Service Desk | Title: IT Service Desk => Branch Operations Support Icon: phoneapp => shield Purpose: System access and technical faults => Go-live weekend and branch-day issues
Support Contacts | 6 | UPDATE | Your Regional Champion | Title: Your Regional Champion => Fraud and Risk Purpose: Local support and floor-walking => Report anything suspicious. The bank never asks for a PIN, password or OTP Contact: [Add name] => [Add contact]
Key Messages | 2 | UPDATE | Smile. Check. Serve. | Title: Smile. Check. Serve. => Same warm welcome. New system. One team.
Key Messages | 3 | UPDATE | Look it up. Share it. Keep banking moving. | Title: Look it up. Share it. Keep banking moving. => Smile. Check. Serve.
Key Messages | 4 | UPDATE | Check together. Start strong. | Title: Check together. Start strong. => Look it up. Share it. Keep banking moving.
Key Messages | 5 | UPDATE | Give customers a head start! | Title: Give customers a head start! => Check together. Start strong.
Key Messages | 6 | UPDATE | Here for your journey | Title: Here for your journey => Never turn a customer away.
Key Messages | 7 | ADD | Give customers a head start! | Title: => Give customers a head start!
Key Messages | 8 | ADD | Here for your journey | Title: => Here for your journey

## Kukua Messages
Title | Text | AudioUrl | Order | IsActive | ACTION
welcome | Hello! I'm Kukua, your Corbit X guide. Between now and go-live on Monday 1 February 2027, I'll help you discover what Corbit X means for our customers, branches, and teams. Let's get started. |  | 1 | Yes | UPDATE
chatFallback | Good question! I don't have an answer for that one yet. Try one of the suggested questions, or check the guide, ask your champion, and log a Command Centre ticket if you are still stuck. |  | 7 | Yes | UPDATE

## Section Intros
Title | Text | Order | IsActive | ACTION
highlights | Look how far we've come together! Our simulation score rose from 51% to 93.4%, and confidence has nearly doubled. | 1 | Yes | UPDATE
next | So, what's next? Here are the five steps that take us from today to go-live on Monday 1 February 2027. | 5 | Yes | UPDATE

## Journey Stages
Title | RailLabel | PosterId | KukuaSays | SecondaryLabel | PanelKukua | PanelIntro | PanelPoints | PanelSay | PanelNote | KeyMessage | Order | IsActive | ACTION
Understanding the Transition | Understanding the Transition | p3 | Customers may have questions about account numbers. Corbit X will introduce changes designed to support a smoother banking experience. This guide helps you confidently support every customer conversation. | Learn More | Here's how to help a customer who arrives with their old account number. | Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and a customer's CIF gains “00” in front. | Look up ¦ Find the new account number in Corbit X using the process covered in training. Serve ¦ Serve the customer and support their transaction. Share ¦ Share the new account number at every interaction. Encourage its use next time. |  | Guidance on printing new account numbers will follow. | <b>Look it up. Share it.</b> Keep banking moving. | 1 | Yes | UPDATE
Chequebook Transition | Cheque Transition | p4 | Chequebook updates can raise customer questions. Understanding the process ensures we provide the right guidance and support. | Quick Tips | My quick tips for cheques that carry old account numbers. | Cheques bearing old account numbers are accepted for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. After that date, these cheques will no longer be accepted. | Accept ¦ Accept old-number cheques until 2 August 2027, subject to the usual checks. Encourage ¦ Encourage customers to request new chequebooks early. Explain ¦ Explain the transition clearly and help customers with their request. |  |  | <b>Give customers a head start!</b> | 2 | Yes | UPDATE
Operational Preparedness | Operational Readiness | p6 | Preparation drives success. Learn how readiness activities help teams operate confidently during key milestones. | Read More | Here's what happens on the Sunday before go-live, and your part in it. | On Sunday 31 January 2027, the day before go-live, BOSs will open the branch day. All branch staff will take part in live transaction and channel checks. | Friday 29 January ¦ Finish all transactions by the 2:00pm cut-off, balance cash and vault, clear suspense and run the final end of day. Test ¦ On Sunday, test deposits, branch transactions, ATMs, the mobile app and other instructed channels. Real funds ¦ These are real transactions with real funds. Follow controls and report issues promptly. Don't close ¦ Do not close the branch day or run end of day on Sunday. Continue ¦ Continue the same branch day into Monday 1 February. Run end of day at the close of business on Monday. |  |  | <b>Check together.</b> Start strong. | 4 | Yes | UPDATE
Keeping Business Moving | Business Continuity | p2 | Business continues while we prepare for change. Discover how we maintain excellent service and support customers throughout the journey. | Best Practices | Account opening pauses for a short while, but our welcome never does. Here's how. | During the static data freeze in the week before go-live and the first three days after go-live (Monday 1 to Wednesday 3 February), account opening is unavailable in Flexcube 11.1 and Corbit X. | Start ¦ Start in Newgen. Collect all required documents. Receive ¦ Receive deposits through the designated GL. Record and monitor every deposit. Finalise ¦ Finalise from Thursday 4 February and provide account numbers. | We are upgrading our systems to serve you better. We can start your application now. Your account number will be provided from Thursday after the upgrade. |  | <b>Never turn away</b> an account-opening request because of the upgrade. | 6 | Yes | UPDATE

## Highlights
Title | Group | Icon | Value | Suffix | ShowBar | Order | IsActive | ACTION
Overall simulation score (95% go-live gate) | Overall readiness | sim | 93.4 | % | Yes | 1 | Yes | UPDATE
Staff confident in go-live readiness (45% at BSIM 1) | Overall readiness | sim | 85 | % | Yes | 2 | Yes | UPDATE
Logged in at BSIM 4 | System and support | check | 99.8 | % | No | 3 | Yes | UPDATE
Tickets fixed the same day | System and support | check | 96 | % | No | 4 | Yes | UPDATE
Branches ready | Branches | users | 94 | % | No | 5 | Yes | UPDATE
Business simulations completed | Branches | users | 4 |  | No | 6 | Yes | UPDATE

## Customer Changes
Title | Points | Alt | Viz | Order | IsActive | ACTION
At the Counter | Quicker service at the counter 360-degree customer view at the teller point Faster credit and salary processing | No | No | 1 | Yes | UPDATE
Account Numbers | New 13-digit account numbers Customer CIF gains “00” in front Old numbers still work for more than six months | Yes | Yes | 2 | Yes | UPDATE
Cheque Books | Reorder within the first 182 days Current leaves accepted in the meantime Books over 5 years old are not migrated | No | No | 3 | Yes | UPDATE
Statements | 0–12 months: straight from Corbit X Older statements, back to account opening: from stored backup | Yes | No | 4 | Yes | UPDATE

## Training Media
Title | Type | Description | Url | Order | IsActive | ACTION
Account opening during the freeze | Video | Start in Newgen, finalise from Thursday 4 February |  | 4 | Yes | UPDATE

## What's Next
Title | Label | Text | Icon | Order | IsActive | ACTION
Keep your skills sharp | 26 Oct – 23 Dec | Practise twice a week. Branches 7:15 – 8:15 am; departments one hour, two days a week. | cap | 1 | Yes | UPDATE
Rest and recharge | 24 Dec – 3 Jan | No scheduled sessions. The Corbit X portal stays open if you want a refresher. | heart | 2 | Yes | UPDATE
Get go-live ready | 4 – 22 Jan | One hour every working day, then certification for your role. | check | 3 | Yes | UPDATE
Final systems check | 11 – 17 Jan | Data migration and validation, then the business simulation on Sunday 17 January. | sim | 4 | Yes | UPDATE
Lift-off! | Mon 1 Feb 2027 | Corbit X goes live. Arrive early, log in and welcome every customer. | rocket | 5 | Yes | UPDATE

## Daily Tips
Title | Order | IsActive | ACTION
Stuck? Check the guide, ask your champion, log a Command Centre ticket, then update the customer. | 9 | Yes | ADD
The bank never asks for a PIN, password or OTP. Never share your login. | 10 | Yes | ADD

## FAQs
Title | Answer | Keywords | Suggested | ActionLabel | ActionTarget | Order | IsActive | ACTION
How will customers benefit? | Quicker service at the counter, a 360-degree customer view at the teller point, faster credit and salary processing, statements for the last 12 months straight from Corbit X and a more secure 13-digit account number. While we transition, old account numbers keep working for more than six months after go-live, and cheques with old numbers are accepted until 2 August 2027. | customers benefit benefits customer better | Yes |  |  | 3 | Yes | UPDATE
What changes for branches? | A few things to know: new account numbers (look them up in Corbit X and share them), cheque and chequebook changes, a short pause in account opening around go-live, and live checks on Sunday 31 January 2027. Each one has a stop on the journey. | branch branches change changes staff operations | Yes | Open the journey | journey | 4 | Yes | UPDATE
Where can I find guides? | Right here! There are six guides on my journey. Tap 'View Guide' on any stop to see the full poster. You will also find guides, staff FAQs and how-to videos on the Corbit X portal on the info portal. | guide guides poster posters find where | Yes | Take me there | journey | 5 | Yes | UPDATE
Who can I contact for support? | Check the guide or FAQ first, then ask your champion or team lead. If you are still stuck, log a Command Centre ticket with a screenshot, and keep the customer updated while you wait. Contact details for the Command Centre will be listed here. | contact support help who phone email | Yes |  |  | 6 | Yes | UPDATE
Will old account numbers still work? | Yes. Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and the CIF keeps the same number with “00” added in front. Look up the new number in Corbit X and share it with the customer. | old account number numbers still work accepted | No | See the guide | stop:1 | 7 | Yes | UPDATE
Can we open accounts during the upgrade? | Account opening pauses during the static data freeze and the first three days after go-live (Monday 1 to Wednesday 3 February). Start the application in Newgen, receive deposits through the designated GL, and finalise from Thursday 4 February. | open opening account new freeze newgen | No | See the guide | stop:6 | 8 | Yes | UPDATE
How do statements work in Corbit X? | Statements for the last 12 months come straight from Corbit X. Older statements, back to when the account was opened, come from stored backup. | statement statements history backup | No |  |  | 9 | Yes | UPDATE
What about cheques? | Cheques with old account numbers are accepted for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. Chequebooks recorded more than five years ago won't be migrated, so help those customers find an approved alternative. Encourage everyone to reorder early. | cheque cheques chequebook chequebooks | No | See the guide | stop:2 | 10 | Yes | UPDATE
What happens on the Sunday before go-live? | On Sunday 31 January 2027, BOSs open the branch day and all branch staff run live transaction and channel checks with real funds. Don't close the branch day or run end of day on Sunday; continue into Monday and run end of day at close of business. | sunday checks testing test weekend live | No | See the guide | stop:4 | 11 | Yes | UPDATE
When does Corbit X go live? | Corbit X goes live on Monday 1 February 2027, in every branch and department at the same time. The final cut-off on the current system is Friday 29 January at 2:00pm. | when date go-live golive live start monday february 2027 cut-off | No | See the guide | stop:4 | 12 | Yes | ADD
How do I read the new account number? | It has 13 digits. Digits 1 and 2 are the currency (00 cedi, 01 dollar, 02 pound, 03 euro). Digit 3 is the customer type (1 individual, 2 non-individual, 3 banks and others). Digits 4 to 11 are a serial number, and digits 12 and 13 are check digits. | account number new 13 digit digits currency customer type format read cif | No |  |  | 13 | Yes | ADD
What if someone asks a customer for their OTP? | The bank never asks for a PIN, password or OTP, and you must never share your login. Tell the customer, and report anything suspicious to Fraud and Risk. | otp pin password fraud scam suspicious login share | No |  |  | 14 | Yes | ADD

## Featured Guides
Title | PosterId | KukuaCommentary | Order | IsActive | ACTION
Keep the Welcome. Start the Process. | p2 | Account opening pauses briefly, but our welcome never does. Start in Newgen and finalise from Thursday 4 February. | 4 | Yes | UPDATE

## Announcements
Title | Body | Icon | Order | IsActive | ACTION
Go-live is now Monday 1 February 2027 | Go-live has moved to accommodate other important transactions the Bank is undertaking. The extra weeks help us go live with even greater confidence. | spark | 1 | Yes | UPDATE
Six Corbit X staff guides are now available | Explore them all on Kukua's journey, from account numbers to go-live readiness. | cap | 2 | Yes | UPDATE
Look-up process included in training | Training covers how to find a customer's new account number in Corbit X. | print | 3 | Yes | UPDATE

## Page Settings
Title | Value | Order | IsActive | ACTION
GoLive | 2027-02-01T00:00:00+00:00 | 1 | Yes | UPDATE
CurrentPhase | 0 | 2 | Yes | UPDATE
AnnouncementTitle | Go-live is now Monday 1 February 2027 | 3 | Yes | UPDATE
AnnouncementBody | Go-live has moved to accommodate other important transactions the Bank is undertaking. The extra weeks help us go live with even greater confidence. See the new calendar in the timeline below. | 4 | Yes | UPDATE
AnnouncementDate | 2026-10-23 | 5 | Yes | UPDATE
FiguresAreIllustrative | No | 6 | Yes | UPDATE

## Staff Guides
Title | PosterId | CatId | Short | Intro | Steps | Key | Say | Note | Order | IsActive | ACTION
Keep the Welcome. Start the Process. | p2 | cx | Account opening during the upgrade. | During the static data freeze in the week before go-live and the first three days after go-live (Monday 1 to Wednesday 3 February 2027), account opening is unavailable in Flexcube 11.1 and Corbit X. | Start ¦ Start in Newgen. Collect all required documents. Receive ¦ Receive deposits through the designated GL. Record and monitor every deposit. Finalise ¦ Finalise from Thursday 4 February 2027 and provide account numbers. | <b>Never turn away</b> an account-opening request because of the upgrade. | We are upgrading our systems to serve you better. We can start your application now. Your account number will be provided from Thursday after the upgrade. |  | 2 | Yes | UPDATE
Old Number? We Can Help! | p3 | acc | Help customers find their new account number. | Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and a customer's CIF gains “00” in front. | Look Up ¦ Look up the new account number in Corbit X using the process covered in training. Serve ¦ Serve the customer and support their transaction. Share ¦ Share the new account number at every interaction. Encourage its use next time. | <b>Look it up. Share it.</b> Keep banking moving. |  | Guidance on printing new account numbers will follow. | 3 | Yes | UPDATE
New Chapter. New Chequebook. | p4 | acc | Cheques with old account numbers. | Accept cheques bearing old account numbers for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. After that date, these cheques will no longer be accepted. | Accept ¦ Accept old-number cheques until 2 August 2027, subject to the usual checks. Encourage ¦ Encourage customers to request new chequebooks early. Explain ¦ Explain the transition clearly and help customers with their request. | <b>Give customers a head start!</b> |  |  | 4 | Yes | UPDATE
Sunday Checks. Monday Confidence. | p6 | ops | Live checks before go-live. | On Sunday 31 January 2027, the day before go-live, BOSs will open the branch day. All branch staff will participate in live transaction and channel checks. | Test ¦ Test deposits, branch transactions, ATMs, the mobile app and other instructed channels. Real Funds ¦ These are REAL transactions with REAL funds. Follow controls and report issues promptly. Do Not Close ¦ Do not close the branch day or run end of day on Sunday. Continue ¦ Continue the same branch day into Monday 1 February. Run end of day at the close of business on Monday. | <b>Check together.</b> Start strong. |  |  | 6 | Yes | UPDATE

## Programme Phases
Title | Icon | When | Description | Focus | Materials | Order | IsActive | ACTION
Keep your skills sharp | cap | 26 Oct – 23 Dec 2026 | Regular practice, so everyone is confident on Corbit X before go-live. | Practise twice a week, every week Branches: 7:15 – 8:15 am. Departments: one hour, two days a week Final session: Wednesday 23 December | h ¦ videos h ¦ qrc p ¦ p3 | 1 | Yes | UPDATE
Rest and recharge | heart | 24 Dec 2026 – 3 Jan 2027 | A break to celebrate with your loved ones. There are no scheduled sessions. | No scheduled sessions Celebrate with your loved ones The Corbit X portal stays open if you want a refresher | h ¦ faq h ¦ videos | 2 | Yes | UPDATE
Get go-live ready | check | 4 – 22 Jan 2027 | One hour every working day (15 days): a refresher, then certification for your role. | Branches: 7:15 – 8:15 am. Departments: time set by your HoD Complete your refresher, then get certified by 22 January Champions check in on your practice; BOSs, BSSMs and HoDs make sure every session happens | h ¦ videos h ¦ qrc p ¦ p3 p ¦ p2 | 3 | Yes | UPDATE
Final systems check | chart | 11 – 17 Jan 2027 | Before lift-off, we make sure every record lands safely in Corbit X. Then we fly a full practice mission together on Sunday 17 January. | Mon 11 Jan: static data migration Wed 13 – Fri 15 Jan: data validation. Sat 16 Jan: financial validation Sun 17 Jan: business simulation (migration plus a full day of business replay) | h ¦ dates h ¦ contacts | 4 | Yes | UPDATE
Lift-off weekend | rocket | Fri 29 Jan – Mon 1 Feb 2027 | Friday 29 January is the last day on the current system, with a 2:00pm cut-off. Sunday 31 January is the live-check day. Monday 1 February is go-live. | Fri 29 Jan: finish all transactions by 2:00pm, balance cash and vault, run the final end of day Sun 31 Jan: BOSs open the branch day and all staff run live checks with real funds. Do not close the day or run end of day Mon 1 Feb: arrive by 7:00am, log in, check printers and apps, welcome every customer and run end of day at close of business | p ¦ p6 p ¦ p1 h ¦ dates | 5 | Yes | UPDATE
After go-live | heart | From Mon 1 Feb 2027 | Support for customers and colleagues through the first days, weeks and months. | Mon 1 – Wed 3 Feb: start account openings in Newgen. Accounts are finalised from Thu 4 Feb First weeks: hypercare, with daily check-ins, the Command Centre on call and champions on the floor Old-number cheques are accepted until 2 August 2027, and old account numbers are still accepted | p ¦ p2 p ¦ p3 p ¦ p4 p ¦ p5 h ¦ contacts | 6 | Yes | UPDATE

## Hub FAQs
Title | Answer | PosterId | Order | IsActive | ACTION
When does Corbit X go live? | Corbit X goes live on Monday 1 February 2027, in every branch and department at the same time. The final cut-off on the current system is Friday 29 January at 2:00pm. | p6 | 1 | Yes | UPDATE
Will customers' old account numbers still work after go-live? | Yes. Old account numbers will continue to be accepted for more than six months after go-live. The new account number has 13 digits, and the CIF gains “00” in front. Look up the new number in Corbit X using the process covered in training, serve the customer, and share the new number so they use it next time. | p3 | 2 | Yes | UPDATE
Can customers still use cheques that show their old account number? | Yes, for six months (182 days) after go-live, until 2 August 2027, subject to the usual checks. After that date these cheques will no longer be accepted, so encourage customers to request new chequebooks early. | p4 | 3 | Yes | UPDATE
What about chequebooks recorded more than five years ago? | These chequebooks will not be migrated to Corbit X and can no longer be used. Affected customers have been notified. Explain the position with care, help them access funds through an approved alternative, and assist with a new chequebook where required. | p5 | 4 | Yes | UPDATE
Can we open new accounts during the upgrade? | Account opening is unavailable in Flexcube 11.1 and Corbit X during the static data freeze (the week before go-live) and for the first three days after go-live (Monday 1 to Wednesday 3 February). Start the application in Newgen, receive deposits through the designated GL, and finalise from Thursday 4 February. Never turn a customer away. | p2 | 5 | Yes | UPDATE
What happens on the Sunday before go-live? | On Sunday 31 January 2027, BOSs will open the branch day and all branch staff take part in live transaction and channel checks: deposits, branch transactions, ATMs, the mobile app and other instructed channels. These are real transactions with real funds. Do not close the branch day or run end of day on Sunday; continue into Monday and run end of day at close of business. | p6 | 6 | Yes | UPDATE
What should I do if I'm not sure how to answer a customer? | Pause and check before answering. Consult the relevant internal team, or find the guidebook or procedure in the repository. Never let a system change become a reason to turn a customer away. | p1 | 7 | Yes | UPDATE
Will new account numbers be printed for customers? | Guidance on printing new account numbers will follow. Until then, look up and share the new number at every interaction. | p3 | 8 | Yes | ADD
How do I read the new account number? | It has 13 digits. Digits 1 and 2 are the currency (00 cedi, 01 dollar, 02 pound, 03 euro). Digit 3 is the customer type (1 individual, 2 non-individual, 3 banks and others). Digits 4 to 11 are a serial number, and digits 12 and 13 are check digits. Always add “00” in front of an existing CIF. | p3 | 9 | Yes | ADD
What should I do if I'm stuck? | Check the repository guide or FAQ, then ask your champion or team lead. If you are still stuck, log a Command Centre ticket with a screenshot, and update the customer while you wait. | p1 | 10 | Yes | ADD
What if someone asks a customer for their OTP? | The bank never asks for a PIN, password or OTP, and you must never share your login. Tell the customer, and report anything suspicious to Fraud and Risk. | p1 | 11 | Yes | ADD

## Training Videos
Title | Description | Order | IsActive | ACTION
Account opening during the freeze | Start in Newgen, finalise from Thursday 4 February | 3 | Yes | UPDATE

## Quick Reference Cards
Title | Items | Order | IsActive | ACTION
Account numbers | + 13 digits: currency (2), customer type (1), serial (8), check (2) + Add “00” before an old CIF + Old numbers accepted for more than six months + Look up and share the new number every time | 1 | Yes | UPDATE
Cheques | + Old-number cheques: six months (182 days), until 2 August 2027, usual checks + Encourage new chequebook requests early - Books recorded 5+ years ago can't be used | 2 | Yes | UPDATE
Account opening | + Start in Newgen, collect all documents + Deposits via the designated GL + Finalise from Thursday 4 February | 3 | Yes | UPDATE
Go-live weekend | + Fri 29 Jan: finish transactions by the 2:00pm cut-off + Sun 31 Jan: live checks with real funds - No branch-day close or EOD on Sunday + Mon 1 Feb: arrive by 7:00am; EOD at close of business | 4 | Yes | UPDATE
Every customer | + Smile & serve. Keep customers informed + Listen calmly; pause and check if unsure - Never turn a customer away - Never share your login, PIN or OTP | 5 | Yes | UPDATE
BOS authorisers | + KYC first (STSKYCMN): search by KYC Reference, not by status + Then CIF (STSCIF): authorise only after the KYC is done + Cheque book request (CASCHBOO): the account must already be open | 6 | Yes | ADD

## Project Updates
Title | Date | Body | Order | IsActive | ACTION
Go-live moves to Monday 1 February 2027 | 2026-10-23 | Go-live has moved to accommodate other important transactions the Bank is undertaking. The extra weeks help us go live with even greater confidence. | 1 | Yes | UPDATE
Staff Guide series complete | 2026-10-19 | All six Corbit X Staff Guide posters are now available in the gallery, covering customer experience, account and chequebook transition, and go-live operations. | 2 | Yes | UPDATE
Account-number look-up included in training | 2026-10-19 | Training covers how to look up a customer's new account number in Corbit X. Complete your modules before go-live. | 3 | Yes | UPDATE
Business simulation 4: 93.4% | 2026-09-20 | Our overall simulation score rose from 51% to 93.4% across four simulations, 1.6 points from the 95% go-live gate. | 4 | Yes | ADD
Printing new account numbers | 2026-10-19 | Guidance on printing new account numbers for customers will follow. Watch this space. | 5 | Yes | ADD

## Key Dates
Title | Body | OffsetDays | OffsetMonths | Format | Big | Order | IsActive | ACTION
Static data migration | Customer and account data moves to Corbit X. | -21 | 0 | Day | No | 1 | Yes | UPDATE
Data validation begins | Every record checked and confirmed, Wednesday 13 to Friday 15 January. | -19 | 0 | Day | No | 2 | Yes | UPDATE
Financial validation | Balances checked to the last pesewa. | -16 | 0 | Day | No | 3 | Yes | UPDATE
Business simulation | Migration plus a full day of business replay. | -15 | 0 | Day | Yes | 4 | Yes | UPDATE
Final cut-off, 2:00pm | Last day on the current system. Balance cash and vault, clear suspense and run the final end of day. | -3 | 0 | Day | No | 5 | Yes | UPDATE
Sunday live checks | BOSs open the branch day; all staff run live transaction and channel checks. Do not close the day or run end of day. | -1 | 0 | Day | No | 6 | Yes | ADD
Corbit X go-live | Arrive by 7:00am. Continue Sunday's branch day; run end of day at close of business. | 0 | 0 | Day | Yes | 7 | Yes | ADD
Account opening resumes | Finalise pending applications and provide account numbers. | 3 | 0 | Day | No | 8 | Yes | ADD
Old-number cheques end | Six months (182 days) after go-live: cheques bearing old account numbers are no longer accepted. | 182 | 0 | Full | Yes | 9 | Yes | ADD

## Support Contacts
Title | Icon | Purpose | Contact | Order | IsActive | ACTION
Your champion | user | First line of help: local support and floor-walking | [Add name] | 1 | Yes | UPDATE
Command Centre | phoneapp | Log a ticket with a screenshot: issues, fixes and coordination | [Add contact] | 2 | Yes | UPDATE
Branch Operations Support | shield | Go-live weekend and branch-day issues | [Add contact] | 3 | Yes | UPDATE
Fraud and Risk | building | Report anything suspicious. The bank never asks for a PIN, password or OTP | [Add contact] | 6 | Yes | UPDATE

## Key Messages
Title | Order | IsActive | ACTION
Same warm welcome. New system. One team. | 2 | Yes | UPDATE
Smile. Check. Serve. | 3 | Yes | UPDATE
Look it up. Share it. Keep banking moving. | 4 | Yes | UPDATE
Check together. Start strong. | 5 | Yes | UPDATE
Never turn a customer away. | 6 | Yes | UPDATE
Give customers a head start! | 7 | Yes | ADD
Here for your journey | 8 | Yes | ADD